## Sheet1
Manufacturing Downtime Project
| tasks | Deliverables | Status
Week 1: Data Cleaning and Preprocessing | oData Preprocessing: Clean and preprocess the data using Power BI | oCleaned dataset ready for analysis.
o Data preprocessing notebook.
Week 2: Analysis Questions Phase | oDetermine Data Analysis Questions: Determine all possible analysis questions that can be deducted from the given dataset and would be of interest to the organization’s decision makers. | o Set of analysis questions that can be answered via the dataset.
oPredict downtime in the next day of operation. Then, accordingly, highlighting the number of batches to be produced.
Week 3: Dashboard Phase | oBuild Dashboard: Build a Power BI dashboard that visualize the answers to the asked questions. | o Power BI dashboard.
Week 4: Final Presentation | o Final Presentation: Prepare a report and presentation summarizing the project work, including data analysis, model development, and deployment. | o Final report and presentation.